Evaluating The Scheduling of The Development Projects of Rural Electricity Network Distribution Using Critical Path Method

Diqbal Satyanegaraa, Widya Nur Bhakti Pertiwib

abFakultas Ekonomi dan Bisnis Universitas Sultan Ageng Tirtayasa, Indonesia

diqbal.s@untirta.ac.id

ABSTRACT. In 2015, PT PLN South Banten Area made a Development Project of Rural Electricity Network Distribution in Banten. This project is held by an electrical installation services company, PT. Z, in June 2015.This project is due 150 days, PT. Z had defined time completion on 143 days, but the completion took 154 days. The type of research used in this research is quantitative research with analytical technique CPM approach. This research identified the least project schedule planning. There are three activities in this project schedule which are unlisted yet, therefore it affected the timeline of the project. Based on the CPM calculation, PT. Z could have shorten the work time down to 3 days with the cost of Rp 1.802.386.000,-.

Keywords: Scheduling, Project, CPM

Introduction

A project has purpose to produce a product with explicitly specified criteria with the allocation of limited resources and took place within a certain time period, which the cost required to complete the project consists of direct and indirect cost (Yulianto, 2013:35). According to Gray & Larson, a project is a complex endeavor, not routine, always constrained by time, budget, resources, and performance specifications that are designed to meet the needs of customers (Mansyur, 2012:6, Yulianto 2013:36). Resource and time limitations, requires a project to be planned and controlled well. In supporting the development of a project, engagement planning both in terms of time, cost, and scope of the project are important (Widiasanti, 2013). However, the result of a planning document is not free of revision as a reference for the stages of implementation and control (Husen, 2011).

Scheduling is step to interpret a palan into a diagaram according to the time scale from the start of the project to be implemented, postpones, and completed, so that financing and resources can be adjusted according to needs (D, Irwan, & Purabasari, 2016). Project plan scheduling describes the activities required for the project in order to achieve the specified target effectively and efficiently. Precision in scheduling will affect the project implementation seriously in order to avoid great loss, such as swelling costs, delays in delivery, and disputes or claims (Widiasanti, 2013).

With the deadline for the project and also the limited resources, often the question of whether the project can be carried out more optimally and economically  arises . To minimize the possibilities of delay, yet the implementation did not go in accordance with the plan set out.

As it happened to PT. Z for construction project of Rural Electricity distribution network, Banten 2015, there is still a gap both in terms of time or cost planning and the implementation of the project by the deadline for completion in of the project based contracts for 150 business days (table 1). The delay in completion of the project can be detrimental to the owner or the company establishing the contract. So, oftentimes, the project period and costs are set a lot more than what had been planned previously.

Table 1. A Comparison Between Planning and Realization

| Company | Due date | Planing | Realization |
| --- | --- | --- | --- |
|  |  | Period (day) | Cost (Rp) | Period (day) | Cost (Rp) |
| PT. Z | 150 days | 143 days | 1.803.421.000 | 154 days | 1.803.421.000 |

source: Data processed by the author

Based on description, then the identified problem of the delay in completing the project will result in the addition of machining time. The occurrence of schedule mismatch made consciously in project planning company in the field resulted with the delayed completion of the project which will have an impact on overtime settlement. As in the project with PT. Z, the original settlement in contract is only 150 working days and it needed to be changed to 154 working days. This means that the project experienced a delay of up to 4 days.

The subject of this research is to examine problems in optimizing machining project time using the CPM AON method on the construction project of Rural Electricity network distribution of 2015 in Banten by PT. Z.

Literature Review

Project Management

The demands and the nature of the project activities are varied, so differences of the managements of each activity are bound to happen, the environment and the atmosphere is relatively stable as a routine operation activities. The management is then called project management. PMI (Project Management Institute) defines project management as a form of science and art related to leading and coordinating the resources that consist of human and material with the use of modern management techniques to achieve the objectives that have been determined, i.e. the scope, quality, schedule, and cost as well as fulfilling the demands of the stakeholders.

According to Turner's (1996) definition of project as "the art and science of turning vision into reality" (Levin, et al, 2018:274). His research on Levin, et al (2018) posited, the Project management process and project outcomes help to develop social ties between the two organizations – client and its agency. Hersanto (2011) argues that project management is a whole activity that uses the principles of management starting from the planning, implementation, and control of the resources to be used in one or more projects with the expectation of benefit (return) on a specific time period. In addition, project management is the activity of planning, organizing, directing, and controlling the company's organizational resources to achieve specific objectives within a specific time with specific resources (Santosa, 2003).

Based on the notion of that sense, it can be concluded that project management is an art and science in conducting planning, organizing, direction and control over the resources that belong to the companies to achieve the goal in a particular time and resources are limited. In project management it needs to be considered so that the output of the project is in accordance with the goals and objectives of the planned, the various problems that may arise when the project was implemented need to be identified. Cost, time, quality, and safety should be in project performance milestones in the process of achieving goals and objectives of the project management (Husen, 2011).

- The cost, the entire sequence of project activities needs to have a standard cost-performance project created with accurate periodic reports made with intent so that overtime can be evaluated and controlled and become a reference in making decisions related to actions of correction in case of irregularities.

- Quality, quality assurance can be obtained by performing a process based on the criteria of material or work which has been determined to come by the standards of the final product. For project work in the future, all the documents of the previous project are re-evaluated to get a better level of efficiency.

- Time, time standard performance is determined by referring to the whole stages of project activities and their duration and use of sources. The results of monitoring reports need to be evaluated and corrected, the trick with the updating of data and information in order to make the performance time achieved according to plan.

- Safety and health work, it is the most important factor in the achievement of the goals of the project. The HSE management system is a structure of complex composition with personnel, resources, programs, along with the policies and procedures that will be integrated in the Organization, container company, or agencies.

Critical Path Method (CPM)

The critical path method is a time-oriented network planning method that is in charge of determining the scheduling and estimation of project completion time which is deterministic (Qomariyah & Hamzah, 2013). The Critical Path Method is carried out in order to get an idea of ​​how the project control process is carried out according to schedule (Caesaron & Thio, 2015). The application of CPM is an effective method in anticipating the problem of excess or lack of time on a project (Yenika Purhariani, 2017). Using CPM can also anticipate the occurrence of cost over run in a project (Siregar & Iffiginia, 2019). Using the Critical Path Method, a project can determine the optimal time and the estimated total cost required (Ulfa & Suhendar, 2021). In line with the research of Utomo & Mulyono (2021), CPM is used to find the most optimal time for rescheduling a construction.

Critical Path Method (CPM) scheduling method is one that makes the assumption that the timing activity was uncertain, and it requires only one factor for each of its activity (Purhariani, et. al. 2017:5). CPM is one type of network schedule work plan or so-called Network Planning is most widely used among all other systems using the principle of the network formation. Drafting the CPM network in the identification of activities as well as using the single time estimate already identified as implementation time. CPM is the first engineering activity network in which diagrams are introduced and developed in 1957 by J.E. Kelly of Remington Rand and M.R. Walker of DuPont Company to assist in the development and the maintenance of the chemical plant in DuPont De Numours & Co. In the CPM system, it determined two estimates of time and cost for each of the activities contained in the work. Both of these estimates are the normal (Normal Estimate) and quick estimations (Crash Estimate) (Hersanto, 2011). The following will explain the terms contained on the CPM, namely:

1. Float or Slack can be defined as a certain amount of time available in an activity so to allow the activity slowdown or delay deliberately or unintentionally, but the delay does not cause the project to become late in completion. Float or Slack will be found after the forward and backward has been  counted completely. Float or Slack is composed of a Total of Float (TF) and Free Float (FF).

- Total Float (TF) is the amount of time an activity is allowed to be postponed, without influencing the overall project schedule. Total Float equals to the time an activity was completed most recently minus the earliest finish time.

Formula: TF = LF – EF = LS – ICE

- Free Float (FF) occurs when all activity on the line corresponding to the start as early as possible. Free Float is equal to the earliest start time (ES) of the next activities minus the earliest finish time (EF) of the activity in question.

2. The critical Path (critical path) is an activity that connects the critical activities. The longest line activities that spilla the part of the activities is the critical path. An activity is said to be critical in the initial time delay will cause a delay in the whole project.

3. Early Start (ES) is the earliest time an activity after activities can be initiated.

4. Late Start (LS) is a period of time an activity can be initiated completed without slowing down the completion of the project schedule.

5. The Early Finish (EF) is the earliest time an activity can be completed if it is begun the earliest and completed in accordance to the time limit.

6. Late Finish (LF) is the most recently activities can be initiated without slowing down the completion of the project.

7. The Earliest Event Time (EET) is the earliest time of the event. To calculate the magnitude of the value of the EET, the use of advanced computation (forward analysis) is needed, starting from the first project activities that connect each activity to the next for the network. If it is found in a long line, it can be added to the time.

Formula: EF = ES + Duration

8. LET (Latest Event Time) is the slowest time of the event. To calculate the magnitude of the value in calculations, use LET retrograde (backward analysis), starting from the most recent activities and to the previous activities.

Formula: LS = LF – Duration

Figure 1. Symbol of Event

Source: Heizer, 2011

CPM comprised Activity On Arrow (AOA) and Activity On Node (AON) methods, which consists of an arrow and a circle or rectangle. Network can be done with experiments based on time boundaries, events, activity, so that the retrieved picture that's worth a raise, the important thing is to show the order of the most sensible and the existence of a reciprocal relationship from one activity to another (Hersanto, 2011).  The symbols used to describe a network in the PERT-type system is as follows:

|  | Circle (node), to define an occurrence or event. The occurrence here is defined as the end of the meeting or of one or several activities. |
| --- | --- |
|  | Arrow (arrow), to declare an activity or activities. The specified activity is an activity that requires a certain period in a number of resource usage (resource, equipment, material, cost). The length or slope of the arrows have no meaning whatsoever. So there is no need to use the scale. The head of the arrow is aiming to the direction that the activity started from the beginning toward the end. |
|  | Arrow disjointed, to declare the pseudo-activities or dummies. Dummies here are used to limit start-up activities. Just like the arrows, the length, thickness, and slope of the dummy does not need to be scaled. The difference with the regular activities is that the dummy does not have a duration or a specific time period for not using or spending the resource. |
|  | The thicker arrows , to declare activities on the critical path. |

Figure 2. A Simple CPM Diagram

Source: Heizer, 2011

- Activity On Arrow (AOA)

Activity On Arrow (AOA) is one of the scheduling methods in a Network Planning that becomes the tool to make a project more effective and efficient (Widisanti, 2013). This method is created by using the arrows to describe the activity or activities, whereas a circle or a square depicting events . The events at the beginning of the arrow is called the node "I", while the event  at the end of the arrow is called node "J", the relation of dependencies are Finish-Start.

Figure 3. The symbol between event in the AOA method

Source: Heizer, 2011

Figure 4. AOA Diagram

Source: Heizer, 2011

- Activity On Node (AON)

Activity On Node (AON) is a scheduling technique that is included in Network Planning in which the activity focuses on node (Widisanti, 2013). In this method, the nodes used are rectangular because it contains more description and arrow simply shows the relationship between the activities. The node usually contains a duration, number of activities, description of activity, ES, EF, LS, and LF.

Figure 5. The symbol between event in the AON method

Source: Heizer, 2011

With the provisions:

- AON must by opening and closing the node node.

- If there are two prodecessor (preliminary node) then the selected largest LF.

- For backward (reverse flow), then the smallest LF was chosen.

- Slack = 0 indicates a critical path as.

Form a network of working with AON method can be seen in the following diagram:

Figure 6. AON Diagram

Source: Heizer, 2011

The framework of Research Model

Organizing a project requires a process of decision-making and goal-setting. Project management sought to establish and coordinate the project goals as well as planning and controlling resources to achieve greater efficiency and effectiveness of project implementation. Planning and controlling the duration of the activities through coordination arrangements to complete the entire job and assignment of resources at the each activity, so that the entire work can be completed efficiently cost and time wise. The goal of the project is usually expressed in the form of savings in production costs and time of completion.

Creating the optimal cost and time is a must for companies, so that the scheduling method must be specified. The policies in setting company should consider both the schedule planning especially time and costs incurred with the total time and cost the company in reality. CPM method is able to determine the time of completion of the project. According to Adedeji and Bello (2014), CPM scheduling is the suitable method for the formulation and management a variety of activities in all construction work, as it provides a schedule that is built based on experience, as well as observations that have been conducted (Ezekiel, et al, 2016; Purhariani, et. al. 2017). With the assumption that the right time will be able to ensure the smooth process of the project, to analyze the relationship between significant time with the success of a project. Based on the description, then an overview of the research of thought framework aims to resolve the problems that exist are directional and structured is shown in Figure 7.

Figure 7. Framework of Research

The purposes of the research conducted were:

- To find out the cause of the delay in the completion of the construction project of Rural Power network distribution Banten 2015 by PT. Z.

- To find out the delayed forecast of the completion of this project if calculated using the CPM method

In science, this research is the development of theories about the CPM which is connected with the reality in the field. These results can be drawn from a new conclusion that can be further developed in the future. Practically, this study contributed for companies to be able to see a variety of things that could still be improved and can specify which activities constitute the critical activities that determines the time of completion of the entire project, so Optimizing the costs incurred by the company for projects that are carried out with the use of CPM.

Research Methods

The type of research used in this research is quantitative research. Bryman (2005) defines the quantitative research process starting from theory, hypothesis, research design, choosing the subject, collecting data, processing data, analyze data, and writing the conclusions (Sujarweni, 2015:39). Based on the level of explanation, the research is classified in a descriptive research. Descriptive research is a research conducted to find out the value of the independent variables, whether one or more, without making comparison or connecting with one another (Sugiyono, 2009). The aim of the research was to make a descriptive description, picture or painting systematically factual and accurate regarding the facts, properties and relationships between the phenomenon examined. In this approach, researches are applied in this, so the purpose of this research is to solve the problems faced by companies implementing the projects in carrying out its activities. Problems encountered is the occurrence of the delay in completing the project.

Operational Definitions Of Variables

Sugiyono (2009) suggests that research is a variable attribute or the nature or value of the persons, objects, or activities which have a certain variation specified by the author to be studied and drawn to the conclusion. Variables are generally divided into two, namely the independent variable and the dependent variable. The variables used in this study i.e. the dependent variable as the optimal time and duration of the project, the dependent relationships between project activities, and budget plan costs as its independent variables.

To simplify the analyzing process then each variable will be defined operationally. The operational definition is elaborating one variable research into the detailed indicators. The operational definitions of variables in this research are as follows:

a. Time optimal project

Time, in this case, is the length of a series when the process takes place, which is a project planning elaboration into a sequence of steps to achieve the target. Optimal project time is the amount of time to complete the project, the best or a relatively short time.

b. the duration of the project

The project duration is the amount of time needed to complete the whole project work.

c. dependent relationships between project activities

Dependent relationships between project activities related to which of the activities must take precedence or worked on and it can be seen that an activity can not be started if the previous activities  not done yet.

These studies use a non-probability sampling, a sampling in which not all samples were given the opportunity to be selected as a the samples to be in use. Samples taken for this research is the development of the Rural Electricity network distribution, a package of 22, by PT. Z.

Data Analysis

The issues facing this project was the time of the completion of the project that is not as planned. Optimization does speed up the duration of the project. The accelerated duration can be done on activities undertaken by the critical path. There are several ways to speed up an activity so that the best alternative was obtained in accordance to the conditions in the field. The analytical technique used in this research is to use CPM approach.

According to Heizer and Render (2011), CPM made the assumption that time is known for sure, so it only takes one time factor for each activity. On the CPM, the "deterministic" way is used i.e. using a numeric estimate. So it's time to finish the job that is considered unknown, then in the next phase, further studies were held to shorten the period of time, for example by adding to the cost or time cost trade-offs or crash the program. The systematics of the process in preparing the network is as follows (Suharto, 1999):

- Reviewing and identifying the scope of the project, outlining, breaking it into an activity or a group of activities is a component of the project.

- Rearranging the components into a chain of the order of the corresponding logic dependency.

- Providing an estimated timeframe for each activity that is produced from the decomposition of the sphere project.

- Identifying the critical path and float on the networks.

The line is a series of activities that relate to one another, starting from the initial node to the end. To complete the project, all paths have to be bypassed. The longest path to determine the total time needed to complete the project. If there is a delay on the longest line, then it will happen late in the project. The longest line of activity is the activity of the critical path, and the longest line is called the critical path. After critical path is known, the next step is to do the acceleration of the project. The steps are as follows:

- To determine the acceleration of time and calculate the acceleration of the surcharge for each activity.

- Speed up the completion of projects with an emphasis on the critical activities that have the lowest cost slope. If the acceleration of the efforts made on activities that are not on the critical path, then the projected overall will not be reduced.

- Stacking back the network that works.

- Repeat steps a second time and stop doing the acceleration efforts in case of a critical path for the increase. Try to avoid going on the addition or removal of critical path if the duration of the acceleration was held at one of the events.

- The acceleration Attempts stopped in activities on the critical path has been completely saturated (not likely pressed again).

- Calculate the acceleration due to the overall cost to find out the total cost of the project is issued

Results

Analysis of Project Scheduling

The following data obtained for the analysis of project scheduling are as follows:

1. Planning of the company

Project planning of the development of the  rural electricity network distribution Banten 2015 is designed by the company started from the predecessor scheduling (table 2) the Gantt chart (Figure 8) shows how long the project is carried out by the company. The predecessor scheduling is a table describing each activity that preceded and activities that precede, or known as relationship activities. Predecessor is useful for planning the project so that the project can run appropriate planning nicely.

Table 2. The Relationship Of Project Activity Of PT Z

| No | Code | Activities | Time (day) | Predecessor | Followers |
| --- | --- | --- | --- | --- | --- |
| 1 |  | Preparation |  |  |  |
|  | A | Survey On Job Sites | 7 | - | B |
|  | B | Procurement Of Materials: MDU dan Non MDU Goods | 30 | A | C |
|  | C | Mobilization of personnel, equipment, Material, Labor and equipment K3 | 3 | B | K |
| 2 |  | Job Network SUTM |  |  |  |
|  | D | Installation Of Traves | 11 | K | E |
|  | E | Installation Of Tupang Drag/Stack Between Taris | 7 | D | F |
|  | F | Wire Withdrawal AAACS 70 mm2 | 7 | E | G |
| 3 |  | Job Network SUTR |  |  |  |
|  | G | Accessories Installation TR | 12 | F | H |
|  | H | Skur Installation TR | 3 | G | I |
|  | I | Wire withdrawal TIC 3 x 35 + N/3 x 50 + N | 9 | H | J |
| 4 | J | Substation jobs Cantol 50 kVA | 45 | I | L |
| 5 | K | Work of the pillars LBS 630 A | 6 | C | D |
| 6 | L | Finishing and administration | 3 | J | - |
| Time of finishing the project | 143 days |

Source: Document of PT. Z

Figure 8. Project Planning Gantt Chart

Not only to do the scheduling, the company also plans the cost budget (table 3). Budget plan costs is the cost of the large number of calculations needed for materials, wages, and other costs related to the implementation of the project. Creating a cost budget means estimating the value of the project early on in order to adjust to the existing budget.

Table 3. Budget Planning PT. Z

| No | Jobs | Volume | Cost (Rp) |
| --- | --- | --- | --- |
| 1 | Transmission |  | 1.029.412.050 |
|  | SUTM |  |  |
|  | Construction SUTM | 5,540 | 246.557.715 |
|  | Wire Materials AAACS 150 mm2 | 9,360 | 259.767.750 |
|  | Wire Materials AAACS 70 mm2 | 7,660 | 120.597.750 |
|  | Pin Post Insulator | 422 | 105.922.000 |
|  | Complete Accessories of Isolator Afspan | 69 | 25.185.000 |
|  | SUTR |  |  |
|  | Construction SUTR | 6,050 | 103.254.235 |
|  | Twisted Cable Materials TIC 3 x 35 + N | 1,580 | 161.300.000 |
|  | Twisted Cable Materials TIC 3 x 50 + N | 4,590 | 150.590.000 |
| 2 | Distribution substation |  | 610.061.600 |
|  | Construction of Distribution subtation 50 kVA | 5 | 298.171.800 |
|  | Supply Errect Substation Materials | 5 | 161.300.000 |
|  | Trafo 3 phasa 50kVA | 5 | 150.590.000 |
|  | Transmission and substation amount |  | 1.639.473.850 |
|  | PPN 10% |  | 163.947.385 |
|  | Total |  | 1.803.421.235 |
|  | Rounding |  | 1.803.421.000 |

Source: document of PT. Z

2. The realization of the Project

The data consists of project realization (table 4 and table 5), Gantt Chart (Figure 9) as well as the realization of project implementation costs (table 5). In the predecessor project realization, there are some jobs that are not listed on the corporate planning it. Such activities are deforestation work, testing, and refinement, and Booths, SUTM SUTR. Following the project realization: predecessor

Tabel 4. Predecessor Project Realization PT. Z

| No | Code | Activities | Time (day) | Predecessor | Followers |
| --- | --- | --- | --- | --- | --- |
| 1 |  | Preparation |  |  |  |
|  | A | Survey On Job Sites | 8 | - | B |
|  | B | Procurement Of Materials: MDU dan Non MDU Goods | 30 | A | C |
|  | C | Mobilization of personnel, equipment, Material, Labor and equipment K3 | 3 | B | D |
| 2 | D | Felling trees | 3 | C | L |
| 3 |  | Job Network SUTM |  |  |  |
|  | E | Installation Of Traves | 11 | L | F |
|  | F | Installation Of Tupang Drag/Stack Between Taris | 7 | E | G |
|  | G | Job Network SUTM | 7 | F | H |
| 4 |  | Installation Of Traves |  |  |  |
|  | H | Accessories Installation TR | 12 | G | I |
|  | I | Skur Installation TR | 3 | H | J |
|  | J | Wire withdrawal TIC 3 x 35 + N/3 x 50 + N | 9 | I | K |
| 5 | K | Substation jobs Cantol 50 kVA | 40 | J | M |
| 6 | L | Work of the pillars LBS 630 A | 6 | D | E |
| 7 |  | Finishing and administration |  |  |  |
|  | M | Checking SUTM, Substation, and SUTR | 10 | K | N |
|  | N | Finishing SUTM, Substation, and SUTR | 5 | M | - |
| Time of finishing the project | 143 days |

Source: Document of PT. Z

Table 5. Project Cost Realization PT. Z

| No | Jobs | Volume | Jumlah Harga(Rp) |
| --- | --- | --- | --- |
| 1 | Transmission |  |  |
|  | SUTM |  |  |
|  | Construction SUTM | 5,540 | 246.557.715 |
|  | Wire Materials AAACS 150 mm2 | 9,360 | 259.767.750 |
|  | Wire Materials AAACS 70 mm2 | 7,660 | 120.597.750 |
|  | Pin Post Insulator | 422 | 105.922.000 |
|  | Complete Accessories of Isolator Afspan | 69 | 25.185.000 |
|  | SUTR |  |  |
|  | Construction SUTR | 6,050 | 103.254.235 |
|  | Twisted Cable Materials TIC 3 x 35 + N | 1,580 | 115.769.500 |
|  | Twisted Cable Materials TIC 3 x 50 + N | 4,590 | 52.331.100 |
| 2 | Distribution substation |  |  |
|  | Construction of Distribution subtation 50 kVA | 5 | 298.171.800 |
|  | Supply Errect Substation Materials | 5 | 161.300.000 |
|  | Trafo 3 phasa 50kVA | 5 | 150.590.000 |
|  | Transmission and substation amount |  | 1.639.473.850 |
|  | PPN 10% |  | 163.947.385 |
|  | Total |  | 1.803.421.235 |
|  | Rounding |  | 1.803.421.000 |

Source: Document of PT. Z

Figure 9. Gantt Chart Realisasi Proyek

The necessary data in this study i.e., schedule and cost planning construction project of Rural Electricity Network Distribution Banten 2015 are obtained from interviews and an examination of the documents of the company. Data obtained processed with CPM using the AON method. After the planning is made by the company and the project is realized in the analysis, the results obtained by processing the data in the form of planning proposals are aimed for the evaluation of the project. Planning the proposal consists of a predecessor proposed scheduling, network diagram by using the method of calculation proposed, as well as AON costs using CPM.

- Proposal of Predecessor Scheduling

Predecessor is a table describing each activity that preceded and activities that precede, or known as the relationship activities. Predecessor is useful for planning the project so that the project can be executed according to good planning. The proposed predecessor scheduling  is made by different authors with the predecessor planning company. This is because the work of deforestation can be carried out simultaneously with the procurement of materials and goods a non MDU without interrupting the critical path of the project. The predecessor proposal can be seen in table 6 below.

Table 6. Predecessor Proposal PT. Z

| No | Code | Activities | Time (day) | Predecessor | Followers |
| --- | --- | --- | --- | --- | --- |
| 1 |  | Preparation |  |  |  |
|  | A | Survey On Job Sites | 8 | - | B |
|  | B | Procurement Of Materials: MDU dan Non MDU Goods | 30 | A | C |
|  | C | Mobilization of personnel, equipment, Material, Labor and equipment K3 | 3 | B | L |
| 2 | D | Felling trees | 3 | A | L |
| 3 |  | Job Network SUTM |  |  |  |
|  | E | Installation Of Traves | 11 | L | F |
|  | F | Installation Of Tupang Drag/Stack Between Taris | 7 | E | G |
|  | G | Job Network SUTM | 7 | F | H |
| 4 |  | Installation Of Traves |  |  |  |
|  | H | Accessories Installation TR | 12 | G | I |
|  | I | Skur Installation TR | 3 | H | J |
|  | J | Wire withdrawal TIC 3 x 35 + N/3 x 50 + N | 9 | I | K |
| 5 | K | Substation jobs Cantol 50 kVA | 40 | J | M |
| 6 | L | Work of the pillars LBS 630 A | 6 | C, D | E |
| 7 |  | Finishing and administration |  |  |  |
|  | M | Checking SUTM, Substation, and SUTR | 10 | K | N |
|  | N | Finishing SUTM, Substation, and SUTR | 5 | M | - |

2. Planning a proposal using the Network Diagram AON

After the predecessor proposal is made, then the next stage is planning a proposal to use the AON network diagram. AON is a network scheduling that is represented by a node (box). The dependency between the activity depicted with arrows between the squares on the AON network. Arrows mark on how associated activities and the order in which some matters to be resolved. The planning is proposed by using the image based predecessor AON network proposal can be seen in Figure 10.

The final condition for the development of Rural Electricity network distribution Banten 2015 with AON to CPM method as follows:

1. Based on the table of the relationships between the activities of planning, then the result of the subsequent data processing done by using the method of AON is on time with the critical path, namely the series of activities of a project that has huge effects on the project undertaken. If one of the activities of the project on the critical path is delayed it may impact other activities.

2. Other results obtained by using the method of AON is that the work that could be done in conjunction with other work, namely deforestation, may reduce the working time of the project. The difference of scheduling PT. Z of 154 days – 151 days = 3 days. From the results (rescheduling), then it can be described as follows:

a. Every activity undertaken can be seen in detail when it is implemented

b. To minimize the activities that take time can extend the time of execution of the project

Conclusion and Suggestion

Conclusion:

Conclusion the results of the analysis using the method of CPM in construction project of Rural Electricity Network Distribution Banten 2015 are:

- The delay in completing of the project is due to the lack of a critical path that is applied on the planning made by their respective companies. In addition, the delay is also caused due to the increase of project work not previously noted in schedule planning.

- There is an actual work that can be done in conjunction with other works without interfering with the critical path. It is deforestation that could be carried out simultaneously with the work of the procurement of materials.

Suggestion:

- In making the network the stages of work should not be wasted, this will slow down the project completion time.

- A network should be done with assisted methods that can support the work on the network, namely with the method of AON (Activity On Node) so that it can shorten the working time of the project.

- The duration of the activities is previously 154 days for PT. Z, having worked with AON method, then the duration can be shortened to 151 days of work, saving the project as much as 3 days.

- Further research is needed with regard to the evaluation of the project costs.

References

Caesaron, D., & Thio, A. (2015). Analisa penjadwalan waktu dengan metode jalur kritis dan pert pada proyek pembangunan ruko (jl. pasar lama no.20, glodok). Journal of Industrial Engineering & Management Systems, 8(2), 59–82.

D, T. B., Irwan, H., & Purabasari, A. (2016). ISSN Cetak : 2301-7244 Analisa Percepatan Proyek Dengan Critical Path Method Pada Proyek Pembangunan Ruang Akomodasi 50pack Awb ( Studi Kasus Pt . Trikarya Alam ) The Analysis Of Accelerate Project For Construction Project Of Accomodation Room 50 Pack Awb. 4(1), 58–67.

Heizer, Jay dan Render, B. (2011). Operation Management, 10th Edition. Boston: Pearson Education.

Hersanto. (2011). Manajemen Proyek. Dinas Pendidikan Provinsi Banten.

Husen, Abrar. (2011). Manajemen Proyek. Yogyakarta: Andi Offset.

Oka, J., & Kartikasari, D. (2019). Evaluasi Manajemen Waktu Proyek Menggunakan Metode Pert Dan Cpm Pada Pengerjaan “Proyek Reparasi Crane Lampson” Di Pt Mcdermott Indonesia. Journal of Applied Business Administration, 1(1), 28–36. https://doi.org/10.30871/jaba.v1i1.1257

Purhariani, Y., Riani, L.P., Meilina, R. (2017). Penerapan CPM dalam Pembangunan Rumah (Studi Kasus Pembangunan Rumah Tipe 36 Ukuran 6 m x 6 m di Jalan Balowerti Nomer 37 Kota Kediri). Simki-Economic. 01, 1-13.

Qomariyah, S., & Hamzah, F. (2013). Analisis Network Planning Dengan Cpm (Critical Path Method) Dalam Rangka Efisiensi Waktu Dan Biaya Proyek. 1(4), 408–416.

Santosa, Budi (2003). Manajemen Proyek. Surabaya: Guna Widya

Siregar, A. C., & Iffiginia, I. (2019). Penggunaan critical path method (CPM) untuk evaluasi waktu dan biaya pelaksanaan proyek. Teknika: Jurnal Sains Dan Teknologi, 15(2), 102. https://doi.org/10.36055/tjst.v15i2.6816

Soeharto, Iman. (1999). Manajemen Proyek (Dari Konseptual Sampai Operasional. Jakarta: Erlangga.

Sugiyono. (2009). Metode Penelitian Bisnis. Bandung: Pusat Bahasa Depdiknas.

Ulfa, S., & Suhendar, E. (2021). Implementasi Metode Critical Path Method Pada Proyek Synthesis Residence Kemang. Jurnal Optimasi Teknik Industri (JOTI), 3(1), 1–6. https://doi.org/10.30998/joti.v3i1.4167

Utomo, F. P., & Mulyono. (2021). Penjadwalan Ulang Proyek Konstruksi Menggunakan Metode PDM dan CPM (Studi Kasus pada Pembangunan Toserba Yogya di Pekalongan). UNNES Journal of Mathematics, 10(1), 62–72.

Widiasanti, Irika dan Lenggogeni. (2013). Manajemen Konstruksi. Bandung: PT Remaja Rosdakarya.

Yenika Purhariani. (2017). PENERAPAN CPM (Critical Path Method) DALAM PEMBANGUNAN RUMAH (Studi Kasus Pembangunan Rumah Tipe 36 Ukuran 6 m x 6 m di Jalan Balowerti Nomor 37 Kecamatan Kota Kota Kediri) THE APPLICABILITY OF CPM (Critical Path Method) IN THE CONSTRUCTIN OF HOUSES (Case. PENERAPAN CPM (Critical Path Method) DALAM PEMBANGUNAN RUMAH (Studi Kasus Pembangunan Rumah Tipe 36 Ukuran 6 m x 6 m Di Jalan Balowerti Nomor 37 Kecamatan Kota Kota Kediri), 01(03), 14.

Yulianto, A. (2013). Optimasi Penjadwalan Proyek Menggunakan CPM dengan Algoritma Genetika pada Studi Kasus Proyek Pembangunan Laboratorium Ekonomi Surabaya. Extrapolasi Jurnal Teknik Sipil Untag Surabaya. 06, 35-42.

# Text boxes

Number of event

Activities

Event

Event

Electric Development Project Planning

Planning & Scheduling Project PT. Z

Evaluation Project Scheduling PT. Z with CPM

Realization PT. Z

Schedule PT. Z

Recommendation of Optimal Schedule Results

Figure 10. Proposal Diagram PT. Z